## Progress summary and 6-month plan

## Scott Veirs

## June 19, 2001

Progress:

Developed new dissertation proposal

Passed general exam on 5/30/01

Implemented initial “puff” model in Matlab

Completed a GFD course during winter quarter, gaining experimental skills and a grade of 3.8

Finished gas chromatograph analysis of Flow Mow fluid samples for H2 and CH4 analytes.

Met once every ~2 weeks to discuss writing progress with Lisa Gilbert

Elected not to apply for a Huckabay fellowship in order to advance research progress

Delivered 1 presentation to the MGG seminar with Fritz Stahr and 1 to the REVEL high school teachers

Prepared and taught a 1-unit seminar on instructional technology in Oceanography

Completed duties as lead teaching assistant, and recruited and trained new lead for upcoming year

Proposed new TA assessment and reward structure

Plan:

June, 2001

# Complete processing of CTD/navigational data and submit with metadata

# Pub1: Help to generate results and figures for MEF heat flux article for G3

# Study site/location map

# Control volume schematic?

# Background casts and q-ness definition

# Animations of subsequent (Dive 51) tops (Dtheta and w) with track distribution

# Parabolic plot of N/S end fluxes, and/or equivalent figure and lateral flux logic

# Help design summer experiments with Thomson and McDuff

# Advise Thomson (June 29 – July 14) and Johnson (June 17 – July 3) cruises

July, 2001

# Pub1: Help to generate draft prose for article on MEF heat flux

# Pub2: Incorporate observed current data into refined puff model

# Examine validity of spatial extrapolation of current meter data

# Resolve lateral currents from ABE MAVS

# Request Thomson (WASP 2000-01) data and inter-compare with other current time series

# Pub3: Initiate GFD laboratory experiments

# Finalize scale and dimensional analysis with Parsons and Wilcock

# Formalize experimental objectives and procedures

# Design and build tank, source, and visualization scheme

August, 2001

# Pub1: Refine article on MEF heat flux

# Pub2: Compare puff model plume distribution with observations

# Pub3: Develop GFD laboratory equipment, visualization, and quantification

September, 2001

# Pub1: Finalize article on MEF heat flux

# Pub2: Calculate instantaneous heat fluxes using observations and puff model

# Pub3: Obtain preliminary results from GFD laboratory experiments

# Help facilitate the New TA Training (Sept. 24/26?)

October, 2001

# Pub1: Submit article on MEF heat flux to G3

# Pub2: Calculate instantaneous heat fluxes using observations and puff model

# Pub3: Conduct quiescent GFD laboratory experiments

November, 2001

# Pub1: Submit article on MEF heat flux

# Pub2: Calculate instantaneous heat fluxes using observations and puff model

# Pub3: Conduct uniform cross flow experiments

December, 2001

# Pub1: Submit article on MEF heat flux

# Pub2: Calculate instantaneous heat fluxes using observations and puff model

# Pub3: Conduct oscillatory cross flow experiments

Present research highlights at the Fall AGU meeting in SF?

Signatures:

_______________________________		______________________________

Russ McDuff					Scott Veirs